## Scope Description
No. | Scope Title | Description | Deliverables
JDBC Connection Convert to API Connection (05/10 – 06/30)
1 | IWS-API-portal Environment Set up | Based on GRBS Database and Staging Database to set-up the IWS Server that to make sure the Restful API can be released by AS400 | Show case for Successfully set-up the IWS Server
2 | IWS-API-portal building | To separate the IWS portal to Current-IWS-API-portal & Staging-IWS-API-portal to make sure the data structure performs the best efficiency. Moreover, based on the service-refactoring result and business requirement to design and build - up the Restful APIs that store in corresponding IWS-API-portals, all the Restful API should pass the API Connection test. | Package & Show case for Current-IWS-API-portal API & Staging-IWS-API-portal API
3 | Service refactoring | First part of Service refactoring is to establish the API connections between IWS-API-Portal and Service, at the start, to analyse the previous JDBC connection data structure and business requirement to design APIs method/request/expect a response, secondary, to file out JDBC - API mapping as the result to let the IWS team create the corresponding APIs on IWS portal, when the APIs ready on IWS, the service APIs connection will be developed to establish connections. The second part is to prepare the IKP migration which needs the data structure should follow the IKP standard. | Function Design Documents, Package, Show case for API connection
4 | API Gateway building | Follow the WPB API-gateway standard to build the API Gateway which handles the tasks involved in accepting and processing up to concurrent API calls, authorization and access control, monitoring. | Function Design Documents, Package
5 | Testing for performance and function correctness | Performance Test: To make sure the performance of IWS connection will be better than JDBC connection. API Connection Test: To make sure all APIs pass the test. SIT & UAT Test &Regression Test: To make sure all the functions shown on Web portal will be the same as previous. | Testing Report
Mobile API Access (07/01 – 09/30)
1 | Customer ID de-code | To communicate with the Mobile App development team to analyze the method to decode the customer ID which is the most significant entity for establishing a connection with Mobile-App and GRBS-App-Engine; when the de-code method confirm, the development team will start developing the de-code method to make sure the Customer ID will be transferred from Mobile App to GRBS-App-Engine. | Function Design Documents, Package, Show case for Customer ID Transfer
2 | Analysis App functions to design the APIs | Follow the business requirement and Mobile App design to finalize the APIs design and development. | Function Design Documents, Package, Show case for Mobile API connection
3 | Testing to make sure performance and correctness of System | Perfomance Test: To make sure the performance of Mobile Apps connect to GRBS-app-engine reach the standard API Connection Test: To make sure all APIs pass the test SIT & UAT Test: To make sure all the functions shown on mobile portal will pass the test case | Testing Report
PCF to IKP migration (07/01 – 09/30)
1 | Analysis the refactoring solutions of the GRBS-App-Engine | Before the refactoring, the analysis will be done that to make sure the GBRS-APP-Engine can be deployed in IKP. | Function Design Documents
2 | GRBS-App-Engine refactoring by using Microservices | For migration of the GRBS-App-Engine to IKP platform, the refactoring will be processed to make sure the data structure will be separated in microservices that can be deployed in IKP. | Package Show Case for Code Structure demo
3 | Deployment the GRBS App-Engine & API Gateway to IKP | When finished the refactoring, the deployment will be processed to make sure all parts of GRBS-App-Engine & API Gateway will run correctly on IKP | Completion/ Sign off to PCF & Completion/ Sign in to IKP
4 | Test the correctness and performance of the platform migration | Performance Test: To make sure the performance of the GRBS-app-engine run in IKP will reach the standard API Connection Test: To make sure all APIs pass the test when migration finished SIT & UAT Test &Regression Test: To make sure all the functions shown on Web portal/Mobile portal will be as same as the previous | Testing Report

## Detail of Scope
Timeline | Tasks
Task 1A:JDBC Connection Convert to API Connection
Sprint 0: (04/19 - 05/07) | Initial Requierment & Source Code analysis
IWS Environment set-up
API Gateway study and set-up
Sprint 1: (05/10 - 06/04) | Development Environment set-up(05/10 - 05/15)
Portal1 &2: Service Refactroring (05/17 - 05/28 )
Portal1 &2: IWS API Building (05/17 - 05/28 )
Unit Test & SIT Test & Regresstion Test (05/31 - 06/04)
Sprint 2: (05/24 - 06/18) | Requirement Analysis(05/24 - 05/28)
Portal3 &4: Service Refactroring (05/31 - 06/11 )
Portal5 &6: IWS API Building (05/31 - 06/11 )
Unit Test & SIT Test & Regresstion Test (06/14 - 06/18)
Sprint 3: (06/07 - 07/02) | Requirement Analysis(06/07 - 06/11)
Portal5 &6: Service Refactroring (06/13 - 06/25 )
Portal5 &6: IWS API Building (06/13 - 06/25 )
Unit Test & SIT Test & UAT Test (06/25 - 07/02)
Task 1B: Mobile API Access
Sprint 0: (06/22 - 07/02) | Communicating with Mobile Team to get requirement
Initial Requierment analysis
Project Plan/Backlog Creatintg
Sprint 1 -Sprint 6 (07/05 - 09/30) | Requirement Analysis
Mobile API build-up
Unit Test & SIT Test & UAT Test
Task 2:PCF to IKP migration
Sprint 0: (06/22 - 07/02) | Migration Solution Confirmation
IKP Study
Initial Requierment analysis
Project Plan/Backlog Creatintg
Sprint 1 -Sprint 6 (07/05 - 09/30) | Requirement Analysis
GRBS app-engine refactoring
Deployment the GRBS App-Engine & API Gateway to IKP
Unit Test & SIT Test & UAT Test

## Cost Team
No | Role | Role Title | Day Rate | Role Title | Day Rate | FT/PT | Skill | Duty | Essential | Working Day | Total Cost | Total Cost
1 | PM | Technology Project Management (GCB4 Equivalent) | 1817.046 | Technology Project Management (GCB5 Equivalent) | 1588.4 | Full Time | Agile/Project Mangement | Analysis/Project Management | √ | 115 | 208960.29 | 182666
2 | Technical Lead/Consulting | Solution Architecture (GCB4 Equivalent) | 2382.926 | Solution Architecture (GCB5 Equivalent) | 1809.8049 | Full Time | Java/Microservice/Spring Cloud/AWS | To refactoring the code structure by using Microservice and help developer to finish Technical attack, same as API Gateway building and Mobile API Technical challenge | √ | 115 | 274036.4946 | 208127.5638
3 | AS400 | Full Stack Engineering (GCB5 Equivalent) | 1337.6 | Full Stack Engineering (GCB7 Equivalent) | 743.204 | Full Time | AS400 | To set-up IWS-API-portal environment and based on refactoring code to design and develop API which store in IWS-API-Portal | √ | 115 | 153824 | 85468.46
4 | Back-end Developer | Development Engineering (GCB5 Equivalent) | 1254 | Development Engineering (GCB7 Equivalent) | 689.7 | Full Time | Java/Spring boot | To refactoring the App-engine-service that replace JDBC connection to Restful API connection Develop the Mobile API after JDBC covertion finished | √ | 115 | 144210 | 79315.5
5 | Back-end Developer | Development Engineering (GCB5 Equivalent) | 1254 | Full Stack Engineering (GCB6 Equivalent) | 1077.2696 | Full Time | Business experience/Java/Spring boot | To analysis the original data structure to file out the data mapping from JPA to Orginal SQL based on business requirement Analysis the Mobile API after JDBC covertion finished | √ | 115 | 144210 | 123886.004
6 | Back-end Developer | Development Engineering (GCB5 Equivalent) | 1254 | Development Engineering (GCB7 Equivalent) | 689.7 | Full Time | Java/Spring boot | To refactoring the App-engine-service that replace JDBC connection to Restful API connection Develop the Mobile API after JDBC covertion finished | √ | 115 | 144210 | 79315.5
7 | Back-end Developer | Development Engineering (GCB5 Equivalent) | 1254 | Full Stack Engineering (GCB6 Equivalent) | 1077.2696 | Full Time | Business experience/Java/Spring boot | To analysis the original data structure to file out the data mapping from JPA to Orginal SQL based on business requirement Analysis the Mobile API after JDBC covertion finished | √ | 115 | 144210 | 123886.004
8 | Tester | Test Engineering (GCB5 Equivalent) | 1086.8 | Test Engineering (GCB7 Equivalent) | 627 | Full Time | Code Experience | Unit Test, API Connection Test and Performance test for IWS/Mobile API/IKP Platform | √ | 115 | 124982 | 72105
9 | Tester | Test Engineering (GCB5 Equivalent) | 1086.8 | Test Engineering (GCB7 Equivalent) | 627 | Full Time | Test Experience | Regression Test for JDBC convertion finished,Moblie API access finished and IKP migration finished. SIT Test for sprint, UAT Test for product release | √ | 115 | 124982 | 72105
Travel expenses | [10 empty] | 50000 | 50000
Net Total | [10 empty] | 1513624.7846 | 1076875.0318
Tax | [10 empty] | 90817.4871 | 64612.5019
Grand Total | [10 empty] | 1604442.2717 | 1141487.5337 | 726401.1578 | 60.84%
Day Cost of Team | [10 empty] | 14695.3863 | 9364.1307
Month Cost of Team | [10 empty] | 337993.8839 | 215375.0064
Month Cost of Team (Include expenses) | [10 empty] | 307267.1672 | 195795.4603
Month Cost of Team (Include profit margin 30%) | [10 empty] | 215087.0171 | 137056.8222
Monthly salary of employees | [10 empty] | 19553.3652 | 15228.5358
Profit Margin | [11 empty] | 24.53%

## Team
No | 职位 | 级别 | 技能 | 职责 | 人选 | 是否招聘 | 成本/月
1 | PM | 中级 | Agile/Project Mangement | 敏捷管理，代码经验，英语书写 | 曾雪松
2 | Technical Lead/Consulting | 高级 | Java/Microservice/Spring Cloud/AWS | 要使用微服务重构代码结构并帮助开发人员完成技术挑战， 包括API网关构建和Mobile API技术实践 | 方弋 | √
3 | AS400/BA | 实习生/文员/BA | AS400 | IWS API 构建，熟悉AS400即可 | 徐曼婷/张芳芳
4 | Back-end Developer | 实习生/初级 | Java/Spring boot | 重构将JDBC连接替换为Restful API连接的App-engine-service JDBC覆盖完成后，开发Mobile API，并根据微服务解决方案，进行系统微服务改造 | 白圣杰
5 | Back-end Developer | 中级 | Business experience/Java/Spring boot | 分析原始数据结构，以根据业务需求提供从JPA到Orginal SQL的数据映射， 在完成JDBC覆盖后分析Mobile API，开发Mobile API,并根据微服务解决方案，进行系统微服务改造 | 王瑞 | √
6 | Back-end Developer | 实习生/初级 | Java/Spring boot | 重构将JDBC连接替换为Restful API连接的App-engine-service JDBC覆盖完成后，开发Mobile API，并根据微服务解决方案，进行系统微服务改造 | 张国娇
7 | Back-end Developer | 中级 | Business experience/Java/Spring boot | 分析原始数据结构，以根据业务需求提供从JPA到Orginal SQL的数据映射， 在完成JDBC覆盖后分析Mobile API，开发Mobile API,并根据微服务解决方案，进行系统微服务改造 |  | √
8 | Tester | 实习生 | Test Experience | 根据User story 撰写User Story, 保存在Jira ;使用测试工具（如Postman）进行API 连通测试 |  | √
9 | Tester | 中级 | Code Experience | 根据User story 撰写User Story, 保存在Jira ;对系统进行整体回归测试,性能测试，功能测试 |  | √

## Ganther
Tasks | Sub-Tasks | Assign | Start Date | Estimate End Date | Status | Duartion (Week) | May | June
Initial Prepare (05/03-06/04) | Team Set-up | Ash | 2021-05-03 | 2021-06-04 | In Progress | 5
| Deploy GRBS in Local Environment | Jason/Rui/Luna | 2021-05-10 | 2021-05-21 | Finished | 2
| GRBS CDMS: Collect SQL with DAO | Jason/Luna | 2021-05-24 | 2021-06-04 | In Progress | 2
| GRBS CDMS: Collect SQL with Service JPA Method | Rui | 2021-05-24 | 2021-06-04 | In Progress | 2
| IWS Environment Set-up | Ash | 2021-05-24 | 2021-05-28 | In Progress | 1
| API Gateway Set-up | Ash | 2021-05-31 | 2021-06-04 | In Progress | 1
| IWS Experiment | Manting/Rui/Ash | 2021-05-31 | 2021-06-04 | Waiting | 1
| GRBS Database design Document collection and learning | Ash | 2021-05-24 | 2021-05-28 | In Progress | 1
| GRBS Confluence page collection and learning | Ash | 2021-05-24 | 2021-06-04 | In Progress | 2
| Database re-set in Local Environment (Optional) | Rui |  |  | Pending | 0
| Solution Design and Project Plan | Waiting for TL |  |  | Pending | 0
Formulas:
Duartion (Week) = ROUNDDOWN(DATEDIF([Start Date],[Estimate End Date],"D")/5,0)

## Detail Schedule
Task | April | [11 empty] | May | [30 empty] | June | [29 empty] | July | [30 empty] | Augest | [30 empty] | September
| 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Task 1A: Sprint 0
Task 1A: Sprint 1
Task 1A: Sprint 2
Task 1A: Sprint 3
Task1B & Task 2: Sprint 0
Task1B & Task 2: Sprint 1
Task1B & Task 2: Sprint 2
Task1B & Task 2: Sprint 3
Task1B & Task 2:Sprint 4
Task 2:Sprint 5
Task 2:Sprint 6
Sprint 0
Environment Set-up
Requirement
Development
Testing
Regression Test & UAT Testing
Task Finished

## Development Step
Step | Description
1 | IWS API Portal building | IWS Environment Set-up | Staging
2 | 找Service中的所有SQL及没有SQL的语句
3 | JPA DAO 翻译成原生SQL(mapping)
4 | 根据整理出来的原生sql做IWS API 构建（按照制定的命名规则）
5 | API 构建完成后，更换Service调动DAO的方法至API
6 | Testing: API 连通测试
7 | 功能测试
8 | Regression 测试
9 | Deployment
10 | UAT Testing

## Analysis
|  | URI | Procedure Identifier | SQL Statement
|  | root/'Functionname' | GET"ENTITY SET" | SELECT "ENTITY","ENTITY","ENTITY"... FORM "LIB" LEFT JOIN ON""... WHERE….
|  | root/'Functionname' | UPDATE'ENTITY SET' | UPDATE "LIB" SET "ENTITY=?","ENTITY=?","ENTITY=?"…WHERE…
|  | root/'Functionname' | REMOVE"ENTITY" | DELETE FROM "LIB" WHERE
|  | root/'Functionname' | ADD | INSERT INTO "LIB"…
Why?
1 | Mobile Portal is developing now
2 | JDBC Connection efficiency can not reach to the expect
3 | Architecture suggest to change JDBC --> API
What?
1 | Phase1: JDBC to API
2 | Phase1: Mobile API
3 | Phase2: Migration system to IKP
When?
1 | Phase1 Before Sep
2 | Phase 2 Before Nov